## Sheet1
Instructions: The Election Timeline Process is a tool to help you plan your election timely. Simply enter your planned election date and the chart will automaticly offer suggestions on the dates that you should conduct the item. You can enter the actually completed dates to track your progress. In the Item colunm there is a detailed list of steps that should be completed to accomplish the item.
| Planned Election Date | 2017-12-01
| Order | Timeline Calc | To Do Date | Actual Completed Date | Item
| 1 | 882 |  | 2015-01-01 | Set up Nominating Committee (start process seven monghs prior to election date) Appoint Officers -Past Chair -Chapter Chairs -Affinity Group Chairs
| 2 |  |  | 2015-05-31 | Deadline to complete Set up of Nominating Committee (start process six months prior to election date)
| 3 | 183 | 2017-06-01 |  | Call for Nominations (complete within 30 days, complete by 30 June) Nominating Committee
| 4 | 154 | 2017-06-30 | 2015-06-30 | Complete Call for Nominations -Solicit all Section members for potential candidates -Members submit nominations
| 5 | 153 | 2017-07-01 | 2015-04-30 | Create Slate (complete no later that 15 October) -Verify eleigbility of member names submitted -Confirm their wilingness to serve -Request Position Statement and Biographies of candidates -For each position select at lease 2 but no more that 3 candidates -Submit slate of candidtates to Section Executive Committee fo ratification
| 6 | 61 | 2017-10-01 |  | Communication to Section Member -Communication slate of candidats to all Section members -Communication process for petition candidates and for write-in candidates
| 7 | 47 | 2017-10-15 |  | Ratified Slate of candidates Complete (Comlete creation of slate)
| 10 | 31 | 2017-10-31 |  | Notification of Ballot (complete communication to Section Memebers using an appropriate medium)
| 15 | 30 | 2017-11-01 |  | Set up Teller Committee (if vTools is used this step is not necessary) Go to http://sites.ieee.org/vtools/ to set up election in vTools 1. Chair submits up to 3 member name to serve on Teller Committee for Section Executive approval 2.Teller Committee reports results to Section Chair after election Set up Election in vTools
** add vtools link here
| 16 | 30 | 2017-11-01 |  | Communicatin Petition Submision Deadline -Notify section member of last day petitions can be accepted
| 17 | 28 | 2017-11-03 |  | Verify Petition Candidate Submissions 1.Verify petitions meet criteria 2. The number of signatures required on a petition shall be determined as follows: For all positions where the electorate is less than 30,000 voting members, signatures shall be required from 2% of the eligible voters. For all positions where the electorate is more than 30,000 voting members, 600 signatures of eligible voters plus 1% of the difference between the number of eligible voters and 30,000 shall be required.” 3. All signers must a member of the section 4. All signers must have provided either their member number or member mailing address 5. All signers of petition must provide their signature. Note: Scanned or electronic signatures are not valid. 6. Verify eligibility of member names submitted 7. Confirm their willingness to serve 8. Request Position Statements and Biographies of petition candidates
| 18 | 27 | 2017-11-04 |  | Finalize Slate -Finalize slate of candidates -Communicate entire slate of canidates to all Section voting members
| 19 | 16 | 2017-11-15 |  | RUN ELECTION
Prepare Ballot to include -Start/end dates -Positions being elected -Candidates by position -Secret ballot
| 20 | 0 | 2017-12-01 |  | Last day for election
| 21 | -2 | 2017-12-03 |  | Confirm Election Results -Tally votes -Report to Section Chair
| 22 | -2 | 2017-12-03 |  | Communication of Election Results - 1. Inform results to each candidate; must contact each candidate before step 2 - 2. Inform Section members - 3. Report results to MGA using vTools officer reporting Click here to report results (http://officers.vtools.ieee.org)
Click here to report results
Formulas:
To Do Date = C3-[Timeline Calc]